## Roadmap
PredictSafeBIO — Customer Readiness Roadmap
Phase | Sprint | Feature / Task | Priority | Effort (days) | Owner | Status | Acceptance Criteria | Notes
Phase 1 | S1 | Configure custom SMTP in Supabase Auth | Critical | 1 | DevOps | Not Started | Signup confirmation email delivered in <60 s; no rate-limit error | Dashboard config — not a code change
Phase 1 | S1 | Re-enable email confirmation | Critical | 0.5 | DevOps | Not Started | New user cannot reach /onboarding until email is confirmed | Remove NEXT_PUBLIC_EMAIL_CONFIRMATION_DISABLED
Phase 1 | S1 | Enable leaked-password protection | High | 0.5 | DevOps | Not Started | Supabase Auth rejects known-breached passwords at signup | Pro plan toggle in dashboard
Phase 1 | S1 | Invite-only access control | Critical | 3 | Dev | Not Started | Signup blocked unless valid invite token exists; owner can generate invite links | Migration + onboarding guard + owner invite UI
Phase 1 | S1 | Password strength indicator on signup | Medium | 1 | Dev | Not Started | UI shows strength meter; blocks submit if < 8 chars or common pattern | Client-side only
Phase 1 | S2 | Full auth smoke test runbook | High | 1 | QA | Not Started | All steps in docs/auth-hardening-runbook.md pass with real inbox
Phase 2 | S2 | Training Matrix — live data read | Critical | 3 | Dev | Not Started | Real training_requirements + assignments shown; demo fallback only when no data | Schema already exists
Phase 2 | S2 | Training Matrix — create/edit requirements | High | 3 | Dev | Not Started | Owner can add/edit training requirement linked to BioType or document
Phase 2 | S2 | Training Matrix — mark completion + evidence upload | High | 3 | Dev | Not Started | Member marks assignment complete; evidence file stored in biotech-documents | Reuse document upload pattern
Phase 2 | S3 | CAPA workflow — list & detail page | High | 3 | Dev | Not Started | /operations/capa shows open CAPAs; detail page shows actions + audit trail | capa_records + capa_actions tables exist
Phase 2 | S3 | CAPA workflow — create / close CAPA | High | 2 | Dev | Not Started | Owner can open CAPA from incident or assessment; member can close with note
Phase 2 | S3 | Inspections page — live scaffold | Medium | 3 | Dev | Not Started | /inspections shows scheduled + completed inspections; create inspection form | Replace placeholder page
Phase 2 | S3 | Document version control — live data | Medium | 3 | Dev | Not Started | /documents/version-control shows real revision history per document | Needs document_versions table migration
Phase 3 | S4 | Member invite flow | Critical | 3 | Dev | Not Started | Owner enters email + role; invite email sent via Supabase Auth invite; acceptee lands on /onboarding with org pre-seeded | workspace_invitations table + SMTP required
Phase 3 | S4 | Team management page | High | 2 | Dev | Not Started | /admin/team lists all members, roles, last-active; owner can remove members
Phase 3 | S4 | Role-based UI enforcement audit | High | 1 | Dev | Not Started | Every owner-only control hidden for members; all actions tested with both roles
Phase 3 | S4 | RLS integration test run | Critical | 2 | QA | Not Started | Two-org test per docs/rls-integration-test-plan.md passes; zero cross-tenant rows
Phase 4 | S5 | Evidence file attachments on evidence map | High | 3 | Dev | Not Started | User can upload a PDF/doc to any compliance_evidence_map row; stored in biotech-documents
Phase 4 | S5 | Structured PDF audit export | High | 3 | Dev | Not Started | Foundation page 'Export' generates PDF: readiness score, evidence map, open gaps, doNotClaim guardrail, owner signoff | Use pdf skill
Phase 4 | S5 | Assessment PDF report | Medium | 2 | Dev | Not Started | Assessment detail 'Download Report' generates structured PDF with score, drivers, recommended actions, guardrail text | Replace current Markdown download
Phase 4 | S6 | Dashboard home page | High | 3 | Dev | Not Started | / or /dashboard shows: readiness score trend, open actions by owner, training expirations, critical/high risk count | Morning check-in view
Phase 4 | S6 | Data deletion flow | Critical | 2 | Dev | Not Started | Owner can request full org data deletion; cascades across all 8 tables + storage | GDPR/CCPA requirement
Phase 4 | S6 | Terms of service acceptance at onboarding | Critical | 1 | Dev | Not Started | New user must accept ToS + Draft-only guardrail acknowledgment before first use
Phase 5 | S7 | LLM draft assist — reviewer note suggestions | Medium | 3 | Dev | Not Started | After status selection, AI offers draft reviewer note; user edits before saving; persists only on explicit submit | Gate: NEXT_PUBLIC_ENABLE_LLM_DRAFT_ASSIST=true
Phase 5 | S7 | LLM draft assist — SOP gap plain-language summaries | Medium | 2 | Dev | Not Started | Gap list items get plain-language AI explanation; labeled Draft - Human Review Required
Phase 5 | S7 | LLM draft assist — audit readiness narrative | Low | 2 | Dev | Not Started | Foundation page shows AI-generated paragraph summarising readiness; human-reviewed before export
Total effort (days) |  |  |  | 56

## Sprint Plan
PredictSafeBIO — Sprint Plan (2-week sprints)
Sprint | Week | Goal | Features in Scope | Deliverable / Demo | Risks | Status
S1 | Wk 1–2 | Auth hardened, invite-only access live | Custom SMTP, email confirmation on, leaked-password protection, invite-only signup, password strength UI | Deployed to Vercel; end-to-end signup + confirmation smoke with real inbox passes | SMTP configuration requires Supabase dashboard access | Not Started
S2 | Wk 3–4 | Training Matrix connected to live data | Training Matrix live read, create/edit requirements, full auth smoke runbook | Owner seeds training requirements; member marks completion; expired badge shown | training_requirements table may need schema additions | Not Started
S3 | Wk 5–6 | CAPA + Inspections + Document versions working | CAPA list/detail/create/close, Inspections scaffold, Document version control | QA team can open and close a CAPA from an assessment; inspection scheduled | Inspections may need new migration for scheduling fields | Not Started
S4 | Wk 7–8 | Multi-user: invite, team management, RLS verified | Member invite flow, team management page, role enforcement audit, RLS test run | Owner invites a second user; both log in; each sees only their org data | Invite flow requires SMTP to be live from S1 | Not Started
S5 | Wk 9–10 | Evidence attachments + PDF reports | Evidence file uploads, structured PDF audit export, assessment PDF report | Auditor-ready PDF downloadable from Foundation and Assessment pages | PDF generation requires pdf skill; audit export may be large | Not Started
S6 | Wk 11–12 | Dashboard, data deletion, ToS acceptance | Dashboard home page, data deletion flow, ToS acceptance at onboarding | First-time user sees ToS; accepts; lands on dashboard; KPI cards populated | Data deletion is irreversible — needs confirmation UX | Not Started
S7 | Wk 13–14 | LLM draft assist (gated) | Reviewer note suggestions, SOP gap plain-language, audit readiness narrative | LLM assist shown as Draft label; user must explicitly save; audit event recorded | Only opens if Phase 1–4 tests are all green and gate doc signed off | Not Started

## Tech Debt
PredictSafeBIO — Tech Debt & Architecture Backlog
Area | Item | Why it matters | Effort | Target sprint | Status
data.ts split | Extract foundation-read-service.ts | getIntelligenceFoundationSummary and 12 other foundation reads still in data.ts (1,400 lines) | 3 days | S2 | Not Started
data.ts split | Extract ergonomic-service.ts | 5 ergonomic functions + 4 helpers still in data.ts | 2 days | S2 | Not Started
data.ts split | Extract map-operations-service.ts | createMapOperationsBundle is 400 lines in data.ts | 2 days | S3 | Not Started
data.ts split | Extract change-plan-service.ts + training-service.ts | Remaining domains to complete the barrel pattern | 1 day | S3 | Not Started
Testing | Unit tests for foundation engine | getIntelligenceFoundationSummary has no test coverage | 2 days | S2 | Not Started
Testing | E2E smoke test automation | Current smoke tests are manual runbooks; automate with Playwright | 3 days | S4 | Not Started
Performance | foundation/page.tsx Suspense boundaries | 7 parallel fetches render all-or-nothing; add per-section Suspense | 2 days | S3 | Not Started
Security | RLS integration test suite (live Supabase) | Unit tests exist; need live two-org integration run per the plan doc | 2 days | S4 | Not Started
Auth | Supabase session refresh handling | Expired JWTs cause silent 401s; add middleware refresh + user-facing error | 1 day | S1 | Not Started
Observability | Error logging (Sentry or similar) | No structured error tracking; production errors only visible in Vercel logs | 1 day | S4 | Not Started
DX | Remove ^ from package.json (done) | Dependencies pinned to exact versions — breaking changes blocked | Done | Done | Done
data.ts split | assessment-service.ts extracted (done) | listAssessments, getAssessmentDetail, updateAssessmentReview, saveAssessment moved | Done | Done | Done
data.ts split | document-service.ts extracted (done) | listDocuments, getDocument, saveDocumentMetadata, persistDocumentRecommendations moved | Done | Done | Done